## V(1)
Project Name:
Proposal Name [Ticket]
Business Requirements:
Enter Business Requirements
Project Work Plan |  |  |  |  | Products and Services
Plan: |  | Hours |  | Quantity | Products and Services (Non-Recurring Fees) | MSRP | Markup | Cost | PPU | Extended Price | Distributor PN | Manufacturer PN
Project Management Services: |  | <Plan Time> |  | Professional Services:
Record project plan in ConnectWise |  |  |  | 10.75 | Affinity Professional Services |  |  |  | 165 | 1773.75
Procurement
Project documentation assignment to PEs |  |  |  | Products:
Knowledge transfer to PEs |  |  |  | 1 | Product 1 |  | 22% | 5 | 6.1 | 6.1 |  | PARTNUMBER
Project coordination with stakeholders |  |  |  |  | Non Recurring Fees Total: |  |  |  |  | 1779.85
Resource scheduling
Determine end user communication plan with client |  |  |  | Quantity | Products and Services (Monthly Recurring Fees) | MSRP | Markup | Cost | PPU | Extended Price | Distributor PN | Manufacturer PN
Prepare for and conduct, project status meetings |  |  |  | Recurring Products:
|  |  |  | 1 | Service 1 |  | 22% | 5 | 6.1 | 6.1 |  | PARTNUMBER
Prepare: |  | Hours |  |  | Monthly Recurring Fees Total: |  |  |  |  | 6.1
Confirm Established Business Requirements: |  | 2.75
Attend internal knowledge transfer meeting |  |  | 1
Review business requirements, proposed services, and solutions
Review product selection |  |  | 0.75
Attend project status meetings |  |  | 1
Determine Affintity Network Standards Alignment Requirements: | 0.5
Determine if Affinity standard VLANs exist:
POS
VOIP
IOT
Data
Guest
ADMIN
Obtain ISP contract information
Determine if a baseline metric for ISP speed exists
Determine if all network equipment is labeled to Affinity Standards
Determin if Patch cable color coding meets Affinity Standards
Create Test Plan: |  |  | 0.25
Create a post cutover core business function test plan
Implement: |  | Hours
Operate: |  | Hours
Implement Affintity Network Standards Alignment: |  | 3
Implement Affinity standard VLANs:
POS
VOIP
IOT
Data
Guest
ADMIN
Record a baseline metric for ISP speed
Label all network equipment to Affinity Standards
Implement Affinity Standard Patch cable color coding
Optimize: |  | Hours
Optimize Solution Configuration: |  | 1
On-site and remote standby support
Resolve operational anomalies
System Optimization: |  | 1
UPDATE: As of 12/8/22 they want us to remove the peer review for now.
[6 empty] | Solution Peer Review: |  |  | 0.25
[6 empty] | Review completed work (Affinity standards) |  |  |  | 0.25 |  |  | Anything above 25 hours this should be an hour.
Report delta to PE
Remediate outstanding nonstandard configurations
Project Closure: |  | 3
Enter configuration documentation into IT Glue and ConnectWise |  |  | 2.25
Knowledge transfer meeting to Affinity technical support staff |  |  | 0.25
Client verification of solution |  |  | 0.25
Notify finance to begin billing of incremental recurring services
Project closure |  |  | 0.25
Estimated Project Services: |  | 10.75
Proposal Notes
Several maintenance windows will be required for solution implementation. If maintenance windows cannot occur during business hours, solution can be implemented after hours. After hours services are not included in this proposal.
Application software vendor assistance will be required to complete this project. Application software vendor professional services fees are not included in this proposal.
If data deletion is requested or required, client will be asked to sign a letter of authorization for data deletion. Additional service charges may result if data cannot be deleted in a timely manner.
Client is responsible for line of business application software licensing. If additional licensing is required, it will be proposed separately.
Fidelity of UNC links and shortcuts to fileserver data will not be preserved in this project. Users may have to recreate shortcuts and links to files. Mapped drives will be preserved.
Proposal contains licensing for Microsoft Windows Server 2019 Standard on (1) physical server containing up to (16) CPU cores and running up to (8) OSEs. If additional licensing is required it will be proposed separately.
Proposal assumes existing domain is fully functional. If troubleshooting of pre-existing issues is required, additional services may be required to complete this project.
This proposal does not address deficiencies in existing backup system. If backup system hardware or software enhancements are required, additional products and services will be required to complete this project.
Proposal assumes backup dataset seeding and additional backup storage are not required. If physical seeding is required, additional products and services will be required to complete this project.
Client must provide installation disks and licensing for applications that need to be installed on new servers. If installation media is not available or ready at the services of deployment, additional services will be required to complete this project.
SSL certificates are not included in this proposal. If required they will be proposed separately.
Power management upgrades have not been included in this proposal. If required, these products will be proposed separately.
Additional AC power connections are not included in this proposal. If required, provisioning of additional AC outlets will be the client's responsibility.
IP scheme design and changes have not been proposed. If required, these services will be proposed separately.
Structured network cabling is not included in this proposal.
Proposal assumes in place cabling is capable of gigabit data transfer rates.
This proposal does not include extensive cable management or cabling cleanup in MDFs and IDFs. If required, additional products and services will be proposed separately.
Disposal and recycling of electronic equipment is not included in this proposal. If required, these services will be proposed separately.
Client assistance with end user communication plan, including direction of the timing of release of communications, will be required.
Client stakeholders must be available to test proposed solutions upon completion of the implementation.
Product availability and pricing cannot be guaranteed at this time. This is due to more frequent price increases, supply chain shortages, and longer lead times for product deliveries. Our team will make every effort to source products at prices proposed and maintain project schedules, and will notify you should any of these factors affect this project.
This proposal does not include shipping and handling charges. These charges, if applicable, will be added to the client invoice.
Proposal does not include applicable taxes. Tax will be added to the client invoices.
This proposal includes a fixed fee for the products and services specified. If additional work is required due to a change in the scope of the client's business requirements, products and/or services, a change order will be submitted to the client for approval, prior to implementation of additional products and services.
This proposal and workplan is protected by copyright under U.S. Copyright Laws and is the property of the original author. You may not copy, reproduce, distribute, publish, display, modify, create derivative works, or transmit this content to any other business, individual, or entity.
IMPORTANT for AZURE AVD HOSTING ONLY- USE NERDIO
For Azure hosting projects use the Nerdio project calculator.
Bundle in Office 365 licensing into the calculator where its needed. https://nmmce.getnerdio.com/
Add Nerdio overhead (difference between azure ) as a AVD management service see this proposal [2280] V3
Do not propose Forensit product as they are using the free version for here on out.
MSP Proposal Notes:
Note1